## Sheet1
0
0 | Project:1 Task:1 Name:Contract signing Duration:0
1 | Project:1 Task:3 Name:Layout definition(VDR) Duration:80
2 | Project:1 Task:4 Name:STRUCTURAL DESIGN Duration:100
3 | Project:1 Task:5 Name:EQUIPMENT DESIGN Duration:190
4 | Project:1 Task:6 Name:FINAL DESIGN REVIEW Duration:0
5 | Project:1 Task:8 Name:Brake Unit Duration:240
6 | Project:1 Task:9 Name:Mechanical miscellany Duration:120
7 | Project:1 Task:10 Name:Electric miscellany Duration:120
8 | Project:1 Task:11 Name:Pneumatic miscellany Duration:120
9 | Project:1 Task:12 Name:ETCS_ ALSTOM Duration:260
10 | Project:1 Task:13 Name:Radio: GSM-R Mesa Duration:240
11 | Project:1 Task:14 Name:TRAFO Duration:1
12 | Project:1 Task:15 Name:ENGINE-CAT Duration:1
13 | Project:1 Task:16 Name:Traction motors & Gearbox Duration:1
14 | Project:1 Task:17 Name:Wires Duration:160
15 | Project:1 Task:18 Name:Axles and Wheels Duration:260
16 | Project:1 Task:19 Name:Bogie Equipment Parts Duration:140
17 | Project:1 Task:20 Name:INDUSTRIALIZATION/METHODS Duration:150
18 | Project:1 Task:22 Name:Iron and Steel pieces(Subcontracting) Duration:80
19 | Project:1 Task:23 Name:Frame structure Duration:100
20 | Project:1 Task:24 Name:Carbody structure manufacturing Duration:20
21 | Project:1 Task:25 Name:1st Loc. Painting Carbody Duration:20
22 | Project:1 Task:27 Name:Bogie structure manufacturing Duration:190
23 | Project:1 Task:28 Name:Bogie equipment Duration:60
24 | Project:1 Task:30 Name:Station 02&03 Piping&Bodyshell Pneumatic Equipment&Wiring Duration:30
25 | Project:1 Task:31 Name:Station 04 Cab &Traction Chain - Assembly Duration:15
26 | Project:1 Task:32 Name:Station 05 Electric/Mechanical connections Duration:15
27 | Project:1 Task:33 Name:Station 06 Hatches assembly Duration:15
28 | Project:1 Task:34 Name:Station 07 Bodyshell on bogies Duration:5
29 | Project:1 Task:36 Name:1st Loc tests(Serial&Type) in Factory Duration:100
30 | Project:1 Task:37 Name:1st Loc tests ETCS/ATC (estimated) Duration:20
31 | Project:1 Task:38 Name:Quality&Finishing Details&Preparation to transport Duration:20
32 | Project:1 Task:39 Name:Customer inspection Duration:1
33 | Project:1 Task:40 Name:Loc 01 Finishing in Factory Duration:0
34 | Project:1 Task:42 Name:Transport to Customer track (Loc 01) Duration:15
35 | Project:1 Task:43 Name:Authorization process (ERA)&Type Approval Duration:180
36 | Project:1 Task:44 Name:Testing acceptance Duration:20
37 | Project:1 Task:45 Name:ACCEPTANCE Loc 01 Duration:0
38 | Project:2 Task:1 Name:Contract signing Duration:0
39 | Project:2 Task:3 Name:Layout definition(VDR) Duration:80
40 | Project:2 Task:4 Name:STRUCTURAL DESIGN Duration:100
41 | Project:2 Task:5 Name:EQUIPMENT DESIGN Duration:190
42 | Project:2 Task:6 Name:FINAL DESIGN REVIEW Duration:0
43 | Project:2 Task:8 Name:Brake Unit Duration:240
44 | Project:2 Task:9 Name:Mechanical miscellany Duration:120
45 | Project:2 Task:10 Name:Electric miscellany Duration:120
46 | Project:2 Task:11 Name:Pneumatic miscellany Duration:120
47 | Project:2 Task:12 Name:ETCS_ ALSTOM Duration:260
48 | Project:2 Task:13 Name:Radio: GSM-R Mesa Duration:240
49 | Project:2 Task:14 Name:TRAFO Duration:1
50 | Project:2 Task:15 Name:ENGINE-CAT Duration:1
51 | Project:2 Task:16 Name:Traction motors & Gearbox Duration:1
52 | Project:2 Task:17 Name:Wires Duration:160
53 | Project:2 Task:18 Name:Axles and Wheels Duration:260
54 | Project:2 Task:19 Name:Bogie Equipment Parts Duration:140
55 | Project:2 Task:20 Name:INDUSTRIALIZATION/METHODS Duration:150
56 | Project:2 Task:22 Name:Iron and Steel pieces(Subcontracting) Duration:80
57 | Project:2 Task:23 Name:Frame structure Duration:100
58 | Project:2 Task:24 Name:Carbody structure manufacturing Duration:20
59 | Project:2 Task:25 Name:1st Loc. Painting Carbody Duration:20
60 | Project:2 Task:27 Name:Bogie structure manufacturing Duration:190
61 | Project:2 Task:28 Name:Bogie equipment Duration:60
62 | Project:2 Task:30 Name:Station 02&03 Piping&Bodyshell Pneumatic Equipment&Wiring Duration:30
63 | Project:2 Task:31 Name:Station 04 Cab &Traction Chain - Assembly Duration:15
64 | Project:2 Task:32 Name:Station 05 Electric/Mechanical connections Duration:15
65 | Project:2 Task:33 Name:Station 06 Hatches assembly Duration:15
66 | Project:2 Task:34 Name:Station 07 Bodyshell on bogies Duration:5
67 | Project:2 Task:36 Name:1st Loc tests(Serial&Type) in Factory Duration:100
68 | Project:2 Task:37 Name:1st Loc tests ETCS/ATC (estimated) Duration:20
69 | Project:2 Task:38 Name:Quality&Finishing Details&Preparation to transport Duration:20
70 | Project:2 Task:39 Name:Customer inspection Duration:1
71 | Project:2 Task:40 Name:Loc 01 Finishing in Factory Duration:0
72 | Project:2 Task:42 Name:Transport to Customer track (Loc 01) Duration:15
73 | Project:2 Task:43 Name:Authorization process (ERA)&Type Approval Duration:180
74 | Project:2 Task:44 Name:Testing acceptance Duration:20
75 | Project:2 Task:45 Name:ACCEPTANCE Loc 01 Duration:0
76 | Project:3 Task:1 Name:Contract signing Duration:0
77 | Project:3 Task:3 Name:Layout definition(VDR) Duration:80
78 | Project:3 Task:4 Name:STRUCTURAL DESIGN Duration:100
79 | Project:3 Task:5 Name:EQUIPMENT DESIGN Duration:190
80 | Project:3 Task:6 Name:FINAL DESIGN REVIEW Duration:0
81 | Project:3 Task:8 Name:Brake Unit Duration:240
82 | Project:3 Task:9 Name:Mechanical miscellany Duration:120
83 | Project:3 Task:10 Name:Electric miscellany Duration:120
84 | Project:3 Task:11 Name:Pneumatic miscellany Duration:120
85 | Project:3 Task:12 Name:ETCS_ ALSTOM Duration:260
86 | Project:3 Task:13 Name:Radio: GSM-R Mesa Duration:240
87 | Project:3 Task:14 Name:TRAFO Duration:1
88 | Project:3 Task:15 Name:ENGINE-CAT Duration:1
89 | Project:3 Task:16 Name:Traction motors & Gearbox Duration:1
90 | Project:3 Task:17 Name:Wires Duration:160
91 | Project:3 Task:18 Name:Axles and Wheels Duration:260
92 | Project:3 Task:19 Name:Bogie Equipment Parts Duration:140
93 | Project:3 Task:20 Name:INDUSTRIALIZATION/METHODS Duration:150
94 | Project:3 Task:22 Name:Iron and Steel pieces(Subcontracting) Duration:80
95 | Project:3 Task:23 Name:Frame structure Duration:100
96 | Project:3 Task:24 Name:Carbody structure manufacturing Duration:20
97 | Project:3 Task:25 Name:1st Loc. Painting Carbody Duration:20
98 | Project:3 Task:27 Name:Bogie structure manufacturing Duration:190
99 | Project:3 Task:28 Name:Bogie equipment Duration:60
100 | Project:3 Task:30 Name:Station 02&03 Piping&Bodyshell Pneumatic Equipment&Wiring Duration:30
101 | Project:3 Task:31 Name:Station 04 Cab &Traction Chain - Assembly Duration:15
102 | Project:3 Task:32 Name:Station 05 Electric/Mechanical connections Duration:15
103 | Project:3 Task:33 Name:Station 06 Hatches assembly Duration:15
104 | Project:3 Task:34 Name:Station 07 Bodyshell on bogies Duration:5
105 | Project:3 Task:36 Name:1st Loc tests(Serial&Type) in Factory Duration:100
106 | Project:3 Task:37 Name:1st Loc tests ETCS/ATC (estimated) Duration:20
107 | Project:3 Task:38 Name:Quality&Finishing Details&Preparation to transport Duration:20
108 | Project:3 Task:39 Name:Customer inspection Duration:1
109 | Project:3 Task:40 Name:Loc 01 Finishing in Factory Duration:0
110 | Project:3 Task:42 Name:Transport to Customer track (Loc 01) Duration:15
111 | Project:3 Task:43 Name:Authorization process (ERA)&Type Approval Duration:180
112 | Project:3 Task:44 Name:Testing acceptance Duration:20
113 | Project:3 Task:45 Name:ACCEPTANCE Loc 01 Duration:0
114 | Project:4 Task:1 Name:Contract signing Duration:0
115 | Project:4 Task:3 Name:Layout definition(VDR) Duration:80
116 | Project:4 Task:4 Name:STRUCTURAL DESIGN Duration:100
117 | Project:4 Task:5 Name:EQUIPMENT DESIGN Duration:190
118 | Project:4 Task:6 Name:FINAL DESIGN REVIEW Duration:0
119 | Project:4 Task:8 Name:Brake Unit Duration:240
120 | Project:4 Task:9 Name:Mechanical miscellany Duration:120
121 | Project:4 Task:10 Name:Electric miscellany Duration:120
122 | Project:4 Task:11 Name:Pneumatic miscellany Duration:120
123 | Project:4 Task:12 Name:ETCS_ ALSTOM Duration:260
124 | Project:4 Task:13 Name:Radio: GSM-R Mesa Duration:240
125 | Project:4 Task:14 Name:TRAFO Duration:1
126 | Project:4 Task:15 Name:ENGINE-CAT Duration:1
127 | Project:4 Task:16 Name:Traction motors & Gearbox Duration:1
128 | Project:4 Task:17 Name:Wires Duration:160
129 | Project:4 Task:18 Name:Axles and Wheels Duration:260
130 | Project:4 Task:19 Name:Bogie Equipment Parts Duration:140
131 | Project:4 Task:20 Name:INDUSTRIALIZATION/METHODS Duration:150
132 | Project:4 Task:22 Name:Iron and Steel pieces(Subcontracting) Duration:80
133 | Project:4 Task:23 Name:Frame structure Duration:100
134 | Project:4 Task:24 Name:Carbody structure manufacturing Duration:20
135 | Project:4 Task:25 Name:1st Loc. Painting Carbody Duration:20
136 | Project:4 Task:27 Name:Bogie structure manufacturing Duration:190
137 | Project:4 Task:28 Name:Bogie equipment Duration:60
138 | Project:4 Task:30 Name:Station 02&03 Piping&Bodyshell Pneumatic Equipment&Wiring Duration:30
139 | Project:4 Task:31 Name:Station 04 Cab &Traction Chain - Assembly Duration:15
140 | Project:4 Task:32 Name:Station 05 Electric/Mechanical connections Duration:15
141 | Project:4 Task:33 Name:Station 06 Hatches assembly Duration:15
142 | Project:4 Task:34 Name:Station 07 Bodyshell on bogies Duration:5
143 | Project:4 Task:36 Name:1st Loc tests(Serial&Type) in Factory Duration:100
144 | Project:4 Task:37 Name:1st Loc tests ETCS/ATC (estimated) Duration:20
145 | Project:4 Task:38 Name:Quality&Finishing Details&Preparation to transport Duration:20
146 | Project:4 Task:39 Name:Customer inspection Duration:1
147 | Project:4 Task:40 Name:Loc 01 Finishing in Factory Duration:0
148 | Project:4 Task:42 Name:Transport to Customer track (Loc 01) Duration:15
149 | Project:4 Task:43 Name:Authorization process (ERA)&Type Approval Duration:180
150 | Project:4 Task:44 Name:Testing acceptance Duration:20
151 | Project:4 Task:45 Name:ACCEPTANCE Loc 01 Duration:0
152 | Project:5 Task:1 Name:Contract signing Duration:0
153 | Project:5 Task:3 Name:Layout definition(VDR) Duration:80
154 | Project:5 Task:4 Name:STRUCTURAL DESIGN Duration:100
155 | Project:5 Task:5 Name:EQUIPMENT DESIGN Duration:190
156 | Project:5 Task:6 Name:FINAL DESIGN REVIEW Duration:0
157 | Project:5 Task:8 Name:Brake Unit Duration:240
158 | Project:5 Task:9 Name:Mechanical miscellany Duration:120
159 | Project:5 Task:10 Name:Electric miscellany Duration:120
160 | Project:5 Task:11 Name:Pneumatic miscellany Duration:120
161 | Project:5 Task:12 Name:ETCS_ ALSTOM Duration:260
162 | Project:5 Task:13 Name:Radio: GSM-R Mesa Duration:240
163 | Project:5 Task:14 Name:TRAFO Duration:1
164 | Project:5 Task:15 Name:ENGINE-CAT Duration:1
165 | Project:5 Task:16 Name:Traction motors & Gearbox Duration:1
166 | Project:5 Task:17 Name:Wires Duration:160
167 | Project:5 Task:18 Name:Axles and Wheels Duration:260
168 | Project:5 Task:19 Name:Bogie Equipment Parts Duration:140
169 | Project:5 Task:20 Name:INDUSTRIALIZATION/METHODS Duration:150
170 | Project:5 Task:22 Name:Iron and Steel pieces(Subcontracting) Duration:80
171 | Project:5 Task:23 Name:Frame structure Duration:100
172 | Project:5 Task:24 Name:Carbody structure manufacturing Duration:20
173 | Project:5 Task:25 Name:1st Loc. Painting Carbody Duration:20
174 | Project:5 Task:27 Name:Bogie structure manufacturing Duration:190
175 | Project:5 Task:28 Name:Bogie equipment Duration:60
176 | Project:5 Task:30 Name:Station 02&03 Piping&Bodyshell Pneumatic Equipment&Wiring Duration:30
177 | Project:5 Task:31 Name:Station 04 Cab &Traction Chain - Assembly Duration:15
178 | Project:5 Task:32 Name:Station 05 Electric/Mechanical connections Duration:15
179 | Project:5 Task:33 Name:Station 06 Hatches assembly Duration:15
180 | Project:5 Task:34 Name:Station 07 Bodyshell on bogies Duration:5
181 | Project:5 Task:36 Name:1st Loc tests(Serial&Type) in Factory Duration:100
182 | Project:5 Task:37 Name:1st Loc tests ETCS/ATC (estimated) Duration:20
183 | Project:5 Task:38 Name:Quality&Finishing Details&Preparation to transport Duration:20
184 | Project:5 Task:39 Name:Customer inspection Duration:1
185 | Project:5 Task:40 Name:Loc 01 Finishing in Factory Duration:0
186 | Project:5 Task:42 Name:Transport to Customer track (Loc 01) Duration:15
187 | Project:5 Task:43 Name:Authorization process (ERA)&Type Approval Duration:180
188 | Project:5 Task:44 Name:Testing acceptance Duration:20
189 | Project:5 Task:45 Name:ACCEPTANCE Loc 01 Duration:0